## Dashboard
IronDev Alpha 0.1 Manual Test Status
Manual test tracker for the Alpha 0.1 product spine: project setup, indexing, chat, tickets, readiness, proposals, safe apply/build/test, traceability, and stale-index recovery. Created 2026-05-17.
Metric | Value | Readiness Gate | Formula | Status | Status | Count
Total tests | 55 | External alpha candidate | All P0 pass, no P0 blocked/fail | Clear | Pass | 0
Pass | 0 | Stale index coverage | All StaleIndex tests pass | Pending | Fail | 0
Fail | 0 | Traceability coverage | Trace area has no P0 fail/block | Clear | Blocked | 0
Blocked | 0 | Safety coverage | Safety area has no P0 fail/block | Clear | In Progress | 0
In Progress | 0 | UI confidence | No P1 UI fail/block | Clear | Not Run | 55
Not Run | 55 | Overall | Manual sign-off required | Pending

## TestMatrix
Comprehensive Manual Test Matrix
Update Status, Owner, Evidence Link, Last Run, and Notes during dogfood and external-alpha readiness testing.
ID | Area | Scenario | Preconditions | Steps | Expected Result | Priority | Status | Owner | Evidence Link | Last Run | Notes
MT-001 | Project Wizard | Create new project skeleton | Fresh workspace; signed in | Open Project Hub; create a new project; enable skeleton; confirm profile detection. | Project is created, profile fields are populated, build/test commands are seeded, and Overview opens. | P0 | Not Run
MT-002 | Project Wizard | Import existing .NET project | Existing BookSeller or small .NET repo | Create/import project using existing path; do not create skeleton. | Project opens with correct local path and no generated files are written. | P0 | Not Run
MT-003 | Project Wizard | Missing path validation | Project path does not exist | Attempt import without skeleton enabled. | Creation is blocked with a clear local path validation message. | P1 | Not Run
MT-004 | Project Profile | Detect profile for .NET repo | Imported .NET repo | Open Project Profile; run Detect/Refresh Profile. | Language, framework, solution file, build/test commands, safe write root, and test framework are populated or warned. | P0 | Not Run
MT-005 | Project Profile | Save and reload project profile | Profile fields edited | Save profile; switch project or restart; reopen profile. | All edited profile fields and commands persist after reload. | P0 | Not Run
MT-006 | Project Profile | Allow Builder Apply toggle controls apply mode | Project profile loaded | Toggle Allow Builder Apply off and on; open Builder for a ticket. | Builder displays proposal-only mode when disabled and allows apply only when enabled and readiness passes. | P0 | Not Run
MT-007 | Indexing | Initial unindexed project warning | Project has no LastIndexedUtc | Open Overview, Chat, Tickets, and Builder entry points. | UI clearly indicates Needs Index before context-dependent actions. | P0 | Not Run
MT-008 | Indexing | Index Now from status pill | Project status Needs Index | Open top status pill; click Index Now. | Index runs, status updates to Ready when files are indexed, and file count is shown. | P0 | Not Run
MT-009 | Indexing | Index failure is visible | Project path points to missing folder | Run Index Project. | Status becomes failure state, details explain missing path, and builder readiness blocks. | P0 | Not Run
MT-010 | Indexing | Ready status requires indexed files | Project has no indexable files | Run Index Project. | Status does not misleadingly show Ready; callout explains no indexable files. | P1 | Not Run
MT-011 | Indexing | Stale index after Builder apply | Ready indexed project and build-ready ticket | Generate proposal; apply it successfully. | Project status changes to Stale Index and Builder readiness blocks next action until re-index. | P0 | Not Run
MT-012 | Chat Context | Chat with fresh project context | Project status Ready | Ask about a specific symbol or file behavior. | Response uses indexed project context and avoids limited-context warning. | P0 | Not Run
MT-013 | Chat Context | Chat warning with stale index | Project status Stale Index | Ask implementation-specific follow-up. | UI and/or response clearly warns that context may be stale. | P0 | Not Run
MT-014 | Chat Context | Follow-up resolves active topic | Prior discussion about persistence | Ask: industry standard? | IronDev treats it as architecture advice for the active persistence topic. | P1 | Not Run
MT-015 | Chat Context | Short confirmation routes correctly | Assistant asked to create ticket or decision | Reply: yes. | IronDev resolves yes against the active pending action. | P1 | Not Run
MT-016 | Tickets | Create ticket from chat | Chat has a clear user request | Use Create Ticket from chat. | Ticket draft opens with title, summary, problem, acceptance criteria, linked context, and generation note. | P0 | Not Run
MT-017 | Tickets | Chat-to-ticket blocks/flags limited context | Project not indexed | Create ticket from chat. | Preflight asks to index first or continue with limited context. | P0 | Not Run
MT-018 | Tickets | Split multiple tickets from chat | Chat request includes multiple distinct work items | Create tickets from chat. | Separate ticket drafts are generated without mixing acceptance criteria. | P1 | Not Run
MT-019 | Tickets | Ticket save/reload | Draft ticket populated | Approve/save ticket; refresh or switch workspace. | Ticket persists with generated fields and selected status/priority. | P0 | Not Run
MT-020 | Tickets | Build This blocked for unclear ticket | Ticket title only, no summary/problem/criteria | Click Build This. | Build readiness blocks with NeedsClarification and actionable message. | P0 | Not Run
MT-021 | Build Readiness | Complete ticket returns ReadyToBuild | Profile, commands, index, and clear ticket exist | Refresh readiness for selected ticket. | Readiness shows ReadyToBuild and builder action is enabled. | P0 | Not Run
MT-022 | Build Readiness | Missing profile blocks builder | No project profile | Attempt Build This. | Readiness blocks with NeedsProjectProfileUpdate. | P0 | Not Run
MT-023 | Build Readiness | Missing build command blocks builder | Profile exists without build command | Attempt Build This. | Readiness blocks with build command missing. | P0 | Not Run
MT-024 | Build Readiness | Open question blocks relevant ticket | OpenQuestion context document exists for ticket area | Attempt Build This. | Readiness blocks and names relevant open question. | P1 | Not Run
MT-025 | Build Readiness | Persistence ticket requires architecture fields | Ticket mentions database; profile lacks DatabaseEngine/DataAccessStyle | Attempt Build This. | Readiness blocks with NeedsArchitectureDecision. | P0 | Not Run
MT-026 | Builder Proposal | Generate safe proposal | Build-ready ticket | Click Build This; wait for Builder Workbench. | Proposal includes summary, rationale, one or more validated file changes, and original request. | P0 | Not Run
MT-027 | Builder Proposal | Incomplete proposal is blocked | LLM returns no changes or invalid file content | Generate proposal. | Validation issues are visible and Apply Proposal is disabled. | P0 | Not Run
MT-028 | Builder Proposal | Proposal matches requested API | Ticket specifies API names/signatures | Generate proposal; review files. | Generated code follows requested API names/signatures or flags uncertainty. | P1 | Not Run
MT-029 | Diff Review | Readable file diff | Proposal generated | Select each proposed file. | Diff view shows file path and readable change content without clipping key text. | P0 | Not Run
MT-030 | Diff Review | Invalid file change callout | Proposal contains invalid path or missing content | Review validation section. | Invalid file and reason are visible in right panel and file list. | P0 | Not Run
MT-031 | Sandbox Apply | Apply requires explicit approval | Valid proposal; AllowBuilderApply true | Click Apply Proposal. | Approval dialog lists project, safe write root, and files before writing. | P0 | Not Run
MT-032 | Sandbox Apply | Cancel approval writes nothing | Approval dialog open | Click No/Cancel. | No files are written and trace records approval cancelled. | P0 | Not Run
MT-033 | Sandbox Apply | SafeWriteRoot enforced | Proposal attempts path outside safe root | Apply proposal. | Apply is blocked with security violation and no outside write occurs. | P0 | Not Run
MT-034 | Build/Test | Successful apply runs build and tests | Valid proposal; build/test commands configured | Approve apply. | Files write, build runs, tests run, statuses and output panels update. | P0 | Not Run
MT-035 | Build/Test | Build failure skips tests | Proposal causes compile failure | Approve apply. | Build output is captured, test status is skipped due to build failure. | P0 | Not Run
MT-036 | Build/Test | Missing test command warning/skip behavior | Build command exists; test command missing | Run readiness and apply flow. | Readiness warns; apply/build behavior clearly shows tests skipped or failed due to configuration. | P1 | Not Run
MT-037 | Architecture Reconciliation | xUnit/MSTest mismatch classified | Build failure caused by generated test framework mismatch | Apply proposal that triggers mismatch. | Reconciliation panel shows failure category, evidence, detected facts, and recommended actions. | P0 | Not Run
MT-038 | Architecture Reconciliation | Accept profile update action | Reconciliation panel visible | Choose profile update action. | Project profile and decision/memory update are saved; trace records action. | P0 | Not Run
MT-039 | Architecture Reconciliation | Cancel reconciliation | Reconciliation panel visible | Choose Cancel. | Panel closes without profile/memory changes and trace records cancellation. | P1 | Not Run
MT-040 | Trace | Proposal generation trace | Generate proposal | Open diagnostics/trace view. | Trace includes readiness evaluation and proposal validation with project/ticket ids and proposed files. | P0 | Not Run
MT-041 | Trace | Apply/build/test trace | Apply proposal | Open diagnostics/trace view. | Trace includes approval, files written, build started/result, test started/result, and final cycle completion. | P0 | Not Run
MT-042 | Trace | Failure trace contains useful error | Build or validation failure occurs | Open trace entry. | Error message is readable and points to validation/readiness/build cause. | P1 | Not Run
MT-043 | Project Memory | Decision creation from chat | Chat contains architecture decision | Create decision from chat and save. | Decision persists with title/detail/category/status/source context where available. | P1 | Not Run
MT-044 | Project Memory | Manual memory editor basic flow | Memory workspace open | Create/edit Project Fact or Open Question. | Typed context document saves, reloads, and influences readiness where relevant. | P1 | Not Run
MT-045 | Project Memory | Project summary visible | Project has summary | Open overview/profile/memory surfaces. | Summary is visible and distinguishable from tickets and decisions. | P2 | Not Run
MT-046 | Context Export | Export context pack | Project has profile, tickets, memory, index status | Run Export Project Context Pack. | Markdown context pack is written and includes index status, profile, decisions, documents, and recent tickets. | P1 | Not Run
MT-047 | BookSeller Boundary | BookSeller remains external sample | BookSeller sandbox configured outside IronDev product repo | Open/import BookSeller as project. | IronDev indexes BookSeller as external project and does not treat it as product source. | P1 | Not Run
MT-048 | Safety | Proposal-only mode blocks apply | AllowBuilderApply false | Generate valid proposal and inspect Apply button. | Apply stays disabled and mode label explains proposal-only mode. | P0 | Not Run
MT-049 | Safety | No writes before approval | Valid proposal generated | Inspect files before clicking apply. | No proposed file content is written until explicit apply approval. | P0 | Not Run
MT-050 | Safety | Recover from failed apply | Apply fails validation or path safety | Attempt apply. | Status explains failure, build/test do not run when unsafe, user can regenerate or fix profile. | P0 | Not Run
MT-051 | UI/Product Feel | Primary workflow discoverability | Fresh alpha user | Create/import project; index; chat; ticket; build readiness; proposal. | User can complete path without hidden commands or developer explanation. | P1 | Not Run
MT-052 | UI/Product Feel | Status callouts are not contradictory | Switch across Overview, Tickets, Builder | Observe index/readiness callouts. | Status and callouts agree across workspaces. | P1 | Not Run
MT-053 | UI/Product Feel | Long paths and diffs remain readable | Project path and filenames are long | Open header, project hub, builder diff. | Text is trimmed/wrapped cleanly without overlap. | P2 | Not Run
MT-054 | Regression | Ready index persists after app restart | Project indexed Ready | Restart app and reopen project. | Status remains Ready with last indexed and file count intact. | P0 | Not Run
MT-055 | Regression | Stale index persists after app restart | Project marked Stale Index | Restart app and reopen project. | Status remains Stale Index and Index Now is available. | P0 | Not Run

## Workflow
End-to-End Workflow Status
Scenario-level test runs that prove the product spine is boring and repeatable before Alpha 0.1 external testing.
ID | Workflow | Execution Path | Expected Outcome | Priority | Status | Owner | Evidence Link | Notes
WF-001 | BookSeller happy path | Import BookSeller, detect profile, index, chat, create ticket, evaluate readiness, generate proposal, review diff. | Ready for apply decision | P0 | Not Run
WF-002 | Full apply/build/test | Starting from WF-001 valid proposal, approve apply, run build and tests, inspect trace. | Files written, output captured, index marked stale | P0 | Not Run
WF-003 | Stale context recovery | After WF-002, verify stale warning, re-index project, regenerate readiness/proposal. | Ready restored after index | P0 | Not Run
WF-004 | Architecture mismatch recovery | Generate proposal with test framework mismatch, apply, inspect reconciliation, approve profile update. | Profile/memory reconcile flow works | P0 | Not Run
WF-005 | Limited context ticket | Use unindexed project, chat, create ticket, choose continue without index. | Ticket is generated with limited-context warning | P1 | Not Run
WF-006 | Safety refusal | Attempt proposal that writes outside SafeWriteRoot. | Apply blocked before write | P0 | Not Run

## StaleIndex
Stale Index Regression Tests
Focused coverage for the highest-priority stabilisation move: every context-dependent action must reveal or block stale index usage.
ID | Check | Precondition | Steps | Expected Result | Status | Owner | Evidence Link | Notes
SI-001 | Initial Ready baseline | Project indexed and IndexedFileCount > 0 | Open Overview and status pill. | Status shows Ready and no stale warning. | Not Run
SI-002 | Apply marks stale | Valid proposal applied successfully | Observe shell status and Overview after apply. | Status shows Stale Index. | Not Run
SI-003 | Builder blocks next action | Project status Stale Index | Attempt to generate or apply another proposal. | Readiness blocks with NeedsReindex. | Not Run
SI-004 | Tickets know context is limited | Project status Stale Index | Create ticket from chat. | Ticket preflight treats context as limited or asks to index first. | Not Run
SI-005 | Index Now visible | Project status Stale Index | Open status pill. | Index Now is visible and actionable. | Not Run
SI-006 | Re-index clears stale | Project status Stale Index | Click Index Now and wait. | Status returns Ready when indexing succeeds. | Not Run
SI-007 | Trace records stale mark | Apply completed | Open trace/diagnostics. | FilesWritten trace says project index marked stale. | Not Run

## DefectLog
Defect Log
Use this as the lightweight bug triage sheet for manual test failures found during Alpha 0.1 dogfood.
ID | Found In Test | Severity | Title | Repro Steps | Expected | Actual | Owner | Status | Notes
D-001
D-002
D-003
D-004
D-005

## Signoff
Alpha 0.1 Manual Sign-off
Final manual readiness checklist for deciding whether IronDev can move from dogfood prototype to external alpha candidate.
Gate | Owner | Decision | Evidence | Date | Notes
Project setup and profile |  | Pending
Index visibility and stale blocking |  | Pending
Chat-to-ticket reliability |  | Pending
Build readiness accuracy |  | Pending
Proposal validation and diff review |  | Pending
Safe apply/build/test sandbox |  | Pending
Traceability usable by tester |  | Pending
Architecture reconciliation |  | Pending
BookSeller external boundary |  | Pending
External alpha go/no-go |  | Pending